## Development Queue
Planned Sprint | Actual Sprint | US ID | User Story Description | Priority | MOSCOW | Estimated Effort (hrs) | Actual Effort (hrs) | Dependency | Assignee | Status
S1 | S1 | US-001 | Gather dataset for credit underwriting from multiple sources. | High | MUST HAVE | 10 | 9 | Kaggle, ChatGPT, Self-made | Suraj Kumar | Completed
S1 | S1 | US-002 | Perform data preprocessing: cleaning, normalization, handling missing values. | High | MUST HAVE | 15 | 14 | Google Colab | Suraj Kumar | Completed
S1 | S1 | US-003 | Conduct initial exploratory data analysis (EDA) with statistical insights. | Medium | SHOULD HAVE | 12 | 11 | Python Libraries | Suraj Kumar | Completed
S2 | S2 | US-004 | Feature engineering and selection to improve model accuracy. | High | MUST HAVE | 18 | 20 | Python Libraries | Suraj Kumar | Completed
S2 | S2 | US-005 | Build and test the initial machine learning model. | Critical | MUST HAVE | 20 | 22 | Python Libraries | Suraj Kumar | Completed

## Active Development Tasks
US ID | Task ID | Task Description | Task Start Date | Task Completion Date | Team Member | Status | Original Estimate (hrs) | Actual Effort (hrs)
US-001 | TASK-001 | Introduction to project and dataset collection. | 2024-12-03 | 2024-12-06 | Suraj Kumar | Completed | 5 | 4.5
US-002 | TASK-002 | Perform data cleaning and handling missing values. | 2024-12-07 | 2024-12-09 | Suraj Kumar | Completed | 8 | 7.5
US-003 | TASK-003 | Perform EDA and generate visual insights. | 2024-12-10 | 2024-12-13 | Suraj Kumar | Completed | 10 | 9.5
US-004 | TASK-004 | Select and engineer features for model training. | 2024-12-15 | 2024-12-18 | Suraj Kumar | Completed | 12 | 11.5
US-005 | TASK-005 | Develop the first machine learning prototype. | 2024-12-20 | 2024-12-25 | Suraj Kumar | Completed | 15 | 14.5

## Lessons Learned
SL # | Sprint # | Sprint start date | Sprint end date | Team member name | Start Doing | Stop Doing | Continue Doing | Action taken
1 | S1 | 2024-12-03 | 2024-12-16 | Suraj kumar | Exploring Drive links for additional resources. | Wasting time debugging without structured approach. | Daily structured learning sessions. | Focused on structured problem-solving approaches.
2 | S2 | 2024-12-16 | 2024-12-24 | Suraj kumar | Implementing advanced preprocessing techniques. | Skipping daily coding practice. | Experimenting with new preprocessing techniques. | Enhanced preprocessing with automation scripts.
3 | S3 | 2024-12-25 | 2025-01-10 | Suraj kumar | Regularly committing changes and documentation. | Procrastination and last-minute coding. | Maintaining workflow discipline. | Improved coding discipline and workflow tracking.
4 | S4 | 2025-01-12 | 2025-01-20 | Suraj kumar | Gaining familiarity with deployment workflows. | Ignoring version control and best practices. | Improving coding efficiency and best practices. | Started using Git effectively for version control.

## Mentor Meeting
Sprint | Day | Impediments | Action Taken
S1 | Day 1 | Introducing to the batch and understanding project scope. | Discussed project scope with mentor.
S2 | Day 2 | Clarifying the project theme and deliverables. | Received detailed explanation on project structure.
S2 | Day 10 | Discussions on AI applications in real-world scenarios. | Conducted team discussions to align expectations.
S3 | Day 15 | Confusion in selecting the right model evaluation metrics. | Researched and implemented best practices for evaluation.
S4 | Day 27 | Challenges in deploying the final model. | Conducted a mentorship session on model deployment.